## Cost Benefit Analysis
Column1 | Costs | 4 Month | 8 Month | 12 Month | Total | Comment
Cost-Benefit Analysis
| [Company Name] | Nilkhet Online Book
| [Proposed Service] | A Web Based Software Cost
| Non-Recurring Costs | 4 Month | 8 Month | 12 Month | Total | Non Recurring Cost: Unusual charge, expense, or loss that is unlikely to occur again in the normal course of a business.
| Hardware |  |  | 60000 | 60000 | Computer, Printer, Sound box, UPS etc
| Servers |  |  | 20000 | 20000 | Dell PowerEdge T130 server
| Software (packaged or custom) |  |  | 30000 | 30000 | Istalled package for backend and frontend with licesense
| Furniture and fixtures |  |  | 20000 | 20000
| Project organizational/support costs |  |  | 20000 | 20000
| Contract negotiations |  |  | 120000 | 120000 | If any employee resign the job
| Labour |  |  | 20000 | 20000
| Development |  |  | 15000 | 15000
| Management |  |  | 20000 | 20000 | Managing the whole development and HR process
| Training of employees (pre-implementation) |  |  | 10000 | 10000
| Post implementation reviews |  |  | 5000 | 5000 | Evaluate the project objectives.
| Total Non-Recurring Costs | 0 | 0 | 340000 | 340000
| Recurring Costs |  |  |  |  | Recurring Cost: This term means the regular cost incurred repeatedly, or for each item produced or each service performed on a recurring or repeated basis.
| Hardware/Software | 80000 | 40000 | 40000 | 160000 | Computer, Printer, Sound box, UPS etc
| Servers | 70000 |  |  |  | Dell PowerEdge T130 server
| Software maintenance and upgrades | 10000 | 10000 | 10000 | 30000 | Maintaing the internal software and service providing through beta version
| Computer supplies | 150000 |  |  | 150000 | Supply 3 computers atleast
| Help Desk support | 20000 | 20000 | 20000 | 60000 | Any kind of requirement and changes implementation
| Ongoing Additional Labour |  |  | 40000 | 40000 | Additional worlflow for implement requirements
| IT staff costs (incl. benefits) | 140000 | 140000 | 140000 | 420000 | Salary and other benefits
| User training |  | 10000 | 10000 | 20000 | User training in every aspects.
| Other |  |  | 20000 | 20000
| Telecommunications | 2500 | 2500 | 2500 | 7500 | Mobille allowance cost
| Office leases | 30000 | 30000 | 30000 | 90000 | Operating expenses
| Total Recurring Costs | 502500 | 252500 | 312500 | 1067500
| Total Costs | 502500 | 252500 | 652500 | 1407500

## Comments
Row 7 | Item details... Include details about specific items to better collaborate with your team. | Diana Ramos | 02/08/16 11:21 PM